## Sheet1
No | Issue | States
1 | when moving item to storage from the inv it feels lagy items like active pet should not move out of inv !! | done
2 | active item should not move out of storage in case the 1 page of the storage is full it should add to the next page up untill the limit of the pages !! ( it seems something wierd after the teleport most of the items are back to inv | partily done
3 | trying to teleport to certen (slat desert) places stuck on loading ! disconnect and reconnect loads normaly game crashed | need to check
4 | 2 chers on the same area crashed the game the ch cher (khaled crashed !!) the eu cher stayed still ! | done
5 | cher loot pickup does not work | done
6 | Fix character deletion and effects | done
7 | sit/walk/run | done
8 | Fix frozen monster hit animation | need test
9 | Fix pet inventory pickup sync | done
10 | Diagnose Magic Pop crash | done
11 | Fix party invite crash | done
12 | right click menu missing | done
13 | party inv works but crashed the game once accepted !!
14 | so first one gone smooth but after first one the game kinda freeze and i cant close or change or move but the world is live but i am stuck/locked ! | done
15 | the game when playing the card i need to re select the item before adding the card other wise it wont put the card .... can we make it atomic ? | working on
16 | Magic POP NPC exchanged coupons one by one instead of exchanging every valid coupon in one click; some gifts remained. Previous opening crash was traced separately. | fixed - need test
17 | exachange between players needs to have confimarion before starting cooldown after the exc on the same player game crashed when the game entered the exchange menu use ide on the client and sr_gameserver for the correct handling
18 | other chers does not see the avater equiped !!
19 | trace option does not work
20 | when the cher attacked an mob while in a party it crashed the game | done
21 | Party reward distribution: picking up 53 gold shows 'distributed to [(null)]' and does not credit party members. EXP is also not shared. Gold must be divided among eligible party members for sharing parties; free-for-all keeps the pickup with the collector. | working on
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98